## Week 2
Timesheet Export
Period: 05/03/2026 to 05/09/2026 Person: Charles Pitts - 41209
Project ID | Project Name | Program ID | Program Name | Work Type | WBS | Work Title | Assigned Hours | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Week Total | Actuals to Date | ETC | Percent Complete | Completion Date | Forecasted Completion Date | Manager Approval Status | PM Approval Status | Timesheet Status | Timesheet Note
54982 | BPR-RFS (Recovery Financial Services) |  |  | Task | 1.2.1 | Project Management Support | 6798 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 4 | 362 | 315 | 52 |  | 2026-08-31 04:00 |  |  | Fully Approved | Attended daily Scrum team meeting, and made updates to work plan for current sprint
54985 | BPR-HK (Healthy Kids) |  |  | Task | 1.8 | Project Assistant Support | 2432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 742 | 37 |  | 2026-06-30 04:00 |  |  | Fully Approved | Auto Populate Time
54994 | EDI Gateway |  |  | Task | 5 | Project Assistant Activities | 8 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 3 | 704 | 556 | 55 |  | 2026-02-27 05:00 |  |  | Fully Approved | Attended weekly team meeting and contributed to the completion of the comparision analysis for leadership
54995 | Enterprise Integration Services (EIS) |  |  | Task | 100.14 | (PMO-OVERARCHING) Project assistance | 16 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 6 | 12 | 0 | 75 |  | 2026-05-14 04:00 |  |  | Fully Approved | Auto Populate Time
55284 | MMT Program Management Support project |  |  | Task | 40.1 | Quality Management Tasks | 14790 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 20 | 1684 | 26 | 97 |  | 2026-12-31 05:00 |  |  | Fully Approved | Continued QA review/edits of RFP changing of formats, text styles, margins, and spacing
55364 | BPR-OES (Office of Eligibility Services) |  |  | Task | 2.4 | Project Assistant Support | 320 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 4 | 52 | 265 | 16 |  | 2026-12-31 05:00 |  |  | Fully Approved | Attended daily scrum team meeting and met with BA to discuss OES EDD team requirements questionaire
55823 | Out of Office and Non-Billable Time |  |  | Task | 1 | Out of Office | 115217.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0.01 | 100 |  | 2026-06-30 04:00 |  |  | Fully Approved | Auto Populate Time
66836 | Program Integrity Solution (SURS 2.0) |  |  | Task | 2.7 | SURS Project Management Activities | 4100 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 3 | 465 | 30 | 93 |  | 2026-06-30 04:00 |  |  | Fully Approved | Attended weekly team meetings discussing use cases with the business team
Totals: | [6 empty] | 143681.06 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 40 | 3964 | 1934.01

## week 3
Timesheet Export
Period: 05/10/2026 to 05/16/2026 Person: Charles Pitts - 41209
Project ID | Project Name | Program ID | Program Name | Work Type | WBS | Work Title | Assigned Hours | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Week Total | Actuals to Date | ETC | Percent Complete | Completion Date | Forecasted Completion Date | Manager Approval Status | PM Approval Status | Timesheet Status | Timesheet Note
54982 | BPR-RFS (Recovery Financial Services) |  |  | Task | 1.2.1 | Project Management Support | 6798 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 5 | 367 | 315 | 53 |  | 2026-08-31 04:00 |  |  | Fully Approved | Attended daily scrum and continued tracking progress of current Sprint
54985 | BPR-HK (Healthy Kids) |  |  | Task | 1.8 | Project Assistant Support | 2432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 742 | 37 |  | 2026-06-30 04:00 |  |  | Fully Approved | Auto Populate Time
54994 | EDI Gateway |  |  | Task | 5 | Project Assistant Activities | 8 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 707 | 556 | 56 |  | 2026-02-27 05:00 |  |  | Fully Approved | Attended weekly team meeting to discuss project risk and executive summary review. Assisted PM with with alternative analysis related for Saas vs MuleSoft
54995 | Enterprise Integration Services (EIS) |  |  | Task | 100.14 | (PMO-OVERARCHING) Project assistance | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 15 | 1 | 100 |  | 2026-05-14 04:00 |  |  | Fully Approved | Attended daily team meetings discussing progress of current sprint and updating work plan
55284 | MMT Program Management Support project |  |  | Task | 40.1 | Quality Management Tasks | 14790 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 20 | 1704 | 26 | 98 |  | 2026-12-31 05:00 |  |  | Fully Approved | Began working through the questions/concerns from leaderships review of the RFP. 1. System availability (uptime 99.9%), (not an SLA as written) 2. Incident and Breach Notification (critical, high) 3. Defect remediation - Sev1 and Sev2 within timeframes 4. Key Major Milestone Deliverables (e.g., project plan, ATO, go-live) 5. Critical Security Patching - time to resolve critical security patches 6. System Performance such as a page load time or transaction time metric 7. Recovery timeline for system restore
55364 | BPR-OES (Office of Eligibility Services) |  |  | Task | 2.4 | Project Assistant Support | 320 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 3 | 55 | 265 | 17 |  | 2026-12-31 05:00 |  |  | Fully Approved | Attended Scrum and continued review of historical documentation of project artifacts.
55823 | Out of Office and Non-Billable Time |  |  | Task | 1 | Out of Office | 115217.06 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 3 | 258 | 0.01 | 100 |  | 2026-06-30 04:00 |  |  | Fully Approved | Auto Populate Time
66836 | Program Integrity Solution (SURS 2.0) |  |  | Task | 2.7 | SURS Project Management Activities | 4100 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 3 | 468 | 29 | 93 |  | 2026-06-30 04:00 |  |  | Fully Approved
Totals: | [6 empty] | 143665.06 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 40 | 4004 | 1934.01

## week 4
Timesheet Export
Period: 05/17/2026 to 05/23/2026 Person: Charles Pitts - 41209
Project ID | Project Name | Program ID | Program Name | Work Type | WBS | Work Title | Assigned Hours | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Week Total | Actuals to Date | ETC | Percent Complete | Completion Date | Forecasted Completion Date | Manager Approval Status | PM Approval Status | Timesheet Status | Timesheet Note
54982 | BPR-RFS (Recovery Financial Services) |  |  | Task | 1.2.1 | Project Management Support | 6798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367 | 315 | 53 |  | 2026-08-31 04:00 |  |  | Fully Approved | Auto Populate Time
54985 | BPR-HK (Healthy Kids) |  |  | Task | 1.8 | Project Assistant Support | 2432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 742 | 37 |  | 2026-06-30 04:00 |  |  | Fully Approved | Auto Populate Time
54994 | EDI Gateway |  |  | Task | 5 | Project Assistant Activities | 8 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 3 | 710 | 556 | 56 |  | 2026-02-27 05:00 |  |  | Fully Approved | Assisted PM with the completion of alternative analysis for leadership.
54995 | Enterprise Integration Services (EIS) |  |  | Task | 97.16 | (PMO-OVERARCHING) Project assistance | 16 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 13 | 3 | 81 |  | 2026-05-22 04:00 |  |  | Fully Approved
54995 | Enterprise Integration Services (EIS) |  |  | Task | 101.15 | (PMO-OVERARCHING) Project assistance | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 2026-05-29 04:00 |  |  | Fully Approved | Auto Populate Time
55284 | MMT Program Management Support project |  |  | Action Log |  |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 10 | 13 |  | 2026-05-18 04:00 |  |  | Fully Approved
55284 | MMT Program Management Support project |  |  | Task | 40.1 | Quality Management Tasks | 14790 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 6 | 1710 | 26 | 98 |  | 2026-12-31 05:00 |  |  | Fully Approved
55364 | BPR-OES (Office of Eligibility Services) |  |  | Task | 2.4 | Project Assistant Support | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 265 | 17 |  | 2026-12-31 05:00 |  |  | Fully Approved | Auto Populate Time
55823 | Out of Office and Non-Billable Time |  |  | Task | 1 | Out of Office | 115217.06 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 24 | 282 | 0.01 | 100 |  | 2026-06-30 04:00 |  |  | Fully Approved | Auto Populate Time
66836 | Program Integrity Solution (SURS 2.0) |  |  | Task | 2.7 | SURS Project Management Activities | 4100 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 469 | 29 | 94 |  | 2026-06-30 04:00 |  |  | Fully Approved
87938 | BPR-GRV (Grievance System) |  |  | Task | 1.2 | Project Management Support | 1000 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 392 | 1 |  | 2026-10-30 04:00 |  |  | Fully Approved | Attended Daily Scrum. Project has been placed on hold until further notice
Totals: | [6 empty] | 144697.06 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 40 | 4040 | 2354.01